## Slide 1
x
Agenda
the
Story
Tamara’s Position
the
Platform
Why this event
the
People
Stakeholder Strategy
the
Engine
Operations & Excecution
the
Proof
ROI & Frameworkds
Most Customer-Centric Financial Super-App on Earth

## Slide 2
BNPL in KSA.
Zero interest. Shariah-compliant.
Built for the 85% without credit cards.
Series C. $340M raised.
$1B valuation. 20M+ customers.
The model proven.
SAMA Consumer Finance License.
First fintech startup in KSA history.
Now a regulated financial institution.
$2.4B — Goldman Sachs, Citi, Apollo.
Largest MENA facility of its kind.
Announced at Money 20/20
Founded
Licensed
2025
Unicorn
2023
SuperApp Era
2020
x
the trajectory is clear...
it just needs a platform

## Slide 3
x
Every audience Tamara needs
under one roof...
Media
Visibility & Global Exposure
Competitors
Global BNPL Players
Merchants
Global Brands
Regulators
Licensing Partners
Investors
Strategic Partnerships
Talent
Employer Branding

## Slide 4
STAKEHOLDER STRATEGY - In Tiers
Strategic
Execution
CEO, Board, Investors
Engagement: Executive dashboard (weekly). Bilateral briefings. Sponsor alignment calls.
Motivation: Brand Optics, Right Vision and Strategy.
Support
External
Marketing, Sales, Product, PR
Engagement: PMO-led workstream calls. Shared project tracker. Creative approvals workflow.
Motivation: Brand consistency. Narrative ownership. Partnerships.
Finance, Legal, HR, Operations
Engagement: Milestone notifications. Budget sign-off checkpoints. Contract review gates.
Motivation: Risk Clearance, Budget Integrity. Staff Management. No Surprises.
Money20/20 Org., Media, Regulators
Engagement: Relationship management via Comms lead. Press briefings. Regulatory pre-clearance.
Motivation: Brand Optics, Right Vision and Strategy.
Weekly 1-page dashboard
Bi-weekly cadences
Cadence depending on milestones & sign-offs
Relationship to be managed
x

## Slide 5
MY OPERATING PRINCIPLES
Start with the Why
Clear Ownership
Seamless Flow Design
Easily Replicable
x
Notes: Narrative before execution — I do not brief the design team until the CMO has approved the story we're telling. The visual identity of our booth, our banners, our digital presence — all of it must serve one coherent message. Dependency-first planning — before I build the timeline, I map the chains. Finding the critical path in Week 1 is planning. Finding it in Week 8 is crisis management. Speed through clarity — the fastest way to slow a project down is ambiguity about ownership. I eliminate that in Week 12. And build once, scale always — this is my direct answer to what a brand-new Communications function needs most. Not just a plan for one event. A system that makes every future event better than the last.

## Slide 6
DEPARTMENT WORKSTREAMS
CEO OFFICE
Narrative approval & keynote final
Announcement decision + CEO briefing pack
On-stage presence + strategic meetings
Keynote → Tahaluf: W8
COMMS & PMO
Master tracker, RACI + communication rhythm
Narrative, press releases + media strategy
Tahaluf interface + all 6 frameworks
Kickoff complete: W12
DESIGN & BRAND
Booth concept (380+ sqm) + all assets
Billboards, flags, banners + digital booth
Tahaluf brand approvals + booth build
All assets → Tahaluf: W6
LEGAL
Announcement legal clearance
Vendor contracts + NDA management
Press release sign-off + final clearances
Announcement cleared: W4
FINANCE
Budget locked + live variance tracker
Vendor payment schedule + contracts
Post-event budget vs actual report
Budget locked: W12
HR & PEOPLE
Employer brand + talent strategy for event
30-pass allocation + travel & accommodation
Staff briefing packs + on-ground coordination
All passes + packs: W1
PRODUCT
Announcement brief + product narrative
Booth demo brief + tech specs
Live product moment on-site (D1)
Brief → Comms: W8
SALES & PR
Merchant target list + pre-event outreach
Execute meetings + same-day CRM logging
Pipeline report + lead categorization → CMO
Pipeline report: P1
x

## Slide 7
E2E PROJECT TIMELINES
PRE-EVENT (12 WEEKS)
IN-EVENT
POST
W12
W11
W10
W9
W8
W7
W6
W5
W4
W3
W2
W1
D1
D2
D3
P1
P2
CEO Office
Sales & PR
Design & Brand
Legal
Finance
HR & People
Product
PMO
⚠ W8: Keynote deadline
⚠ W6: Asset submission
⚠ D1: 15-min announcement sequence
R /A /C /I Matrix
Project Master Timeline
x
Notes: Full project timeline — 17 columns, 8 departments, color-coded. Three risk flags mark the no-miss milestones. Week 8 — CEO keynote topic confirmed with Tahaluf's speaking coordinator or we lose the speaking slot. Week 6 — all physical design assets submitted for Tahaluf brand approval. Their review takes 2 weeks minimum. Day 1 — the announcement sequence: stage, press release, social, media — coordinated in 15 minutes. That requires Legal, PR, Social, and CEO Office aligned days before, not hours. PMO runs the full width — present and accountable from Week 12 through the post-event close, including building the operating system frameworks in P1 and P2. The MOU documentation in P1 captures any partnerships or deals initiated at the event for formal follow-up.
7

## Slide 8
EVENT EXECUTION STRATEGY
EVENT CHECKLIST
Live announcement with CEO on stage
Media coverage active
CEO & Tamara LinkedIn post live
Booth operational — AV, demo, staff positioned
Pre-scheduled meetings confirmed
CRM entries up to date
All Founding Partner deliverables activated
Team debrief confirmed
POST-EVENT: CLOSE IT STRONG
Deliverable
Target
Full media coverage report (volume, tier, reach, sentiment)
Day 3
Social amplification — CEO clips, announcement highlights
Days 1-3
CRM update — all leads and conversations captured
Day 2
Budget vs actual final report
Day 7
Tahaluf post-event email campaign (Founding Partner benefit)
Day 10
Post-event leadership report (ROI vs pre-agreed targets)
Day 7
Partnership + MOU formal documentation
Day 7
TOOLS FOR FUTURE
1. Lessons Learned Log 2. ROI Dashboard 3. Sponsorship Evaluation Scorecard
15 days
post
x

## Slide 9
ROI FRAMEWORK
Every metric agreed before the event. Every target justified. Every result accountable.
ROI Interactive Dashboard
Booth Visitors
Meetings held
Qualified Leads
Deals Closed
Attendees reached
  Brand
  Operations
  Commercial
  Strategic
x
Notes: ROI is only meaningful if agreed before the event — not assessed retrospectively to make it look good. I'd propose these four categories and specific targets to the CMO in Week 12. So that every decision in the 12-week plan can be tested: does this move these numbers? Brand ROI tells us how the story landed. Commercial ROI tells us whether the event generated real business momentum. Operational ROI tells us whether I did my job — budget under 5% variance, all 30 Founding Partner benefits activated. Strategic ROI tells us whether we moved the needle with the audiences that define Tamara's future. I'll flag one specific metric: the shift from 'BNPL company' to 'financial super-app' in how media describes Tamara. That's what we're trying to achieve. That's the measure of whether the narrative landed.
11

## Slide 10
TAMARA · PMO COMMUNICATIONS · QADR ARSLAN
0
1
100x
ambiguity
plan
impact
Notes: Everything in this plan serves one outcome — a Tamara that shows up at Money 20/20 not as a sponsor buying visibility, but as the defining company of GCC fintech declaring its next chapter. The operational system I've built — the stakeholder architecture, the 12-week plan, the in-event playbook, the ROI framework, the operating manual — all of it exists to protect one thing: the story. Because Tamara has earned the right to tell it. my job is to ensures Tamara doesn’t just attend Money20/20 — it leads the conversation! Thank you.